Independent Monitoring Association for Child Labour (IMAC)

#### Forty Eight Progress Report

(01 March    –   31 March 2007)

General:

The total number of manufacturers who have joined Child Labour elimination Programme are 132, after taking the 47 manufacturers out who were removed from the programme due to the non-payment of their dues to the SCCI, the total number of soccer ball manufacturers active in the programme are 85. From this, 63 manufacturers are in IMAC’s main database whereas 22 are in the provisional list.

Monitoring Progress:

During the reporting period, the IMAC monitors carried out 1,629 monitoring visits of 58 manufacturers out of the 3,500 operational centers. This included 08 manufacturers from the list of provisional members. Altogether 22  manufacturers are in the provisional list. They do not have enough work in hand and their stitching centers are either closed or they function occasionally or they have recently joined the programme. This does not provide enough opportunity to the IMAC monitors to judge their real performance. As soon as the IMAC is satisfied with the performance of these manufacturers, they shall be included in the main monitoring database.

Of the total 3,500 operational centers of the participating manufacturers, 1,750 were small village-based centers, 399  were exclusively female centers, 206 were combined and rest of the 1,145 centers were male. Out of the 1,629 centers visited in the month of  March, 491 were male centers, 167 were female centers, 96 were combined and 875 were small village based centers. While visiting the stitching centres outside Sialkot district, the IMAC monitored 218 centers of 24 manufacturers with 1,421 stitchers located in the districts of Gujranwala, Gujrat, Narowal, Hafiz Abad and Sheikhupura.

Based on the IMAC criterion of ABC performance list, 61 manufacturers, are part of IMAC’s main database “A” list whereas two manufacturers M/S Mallhi Sports and M/S Orpheus Enterprises (Pvt) Ltd maintained their status in category “C”.

Working Conditions in the Stitching Centres Monitored by IMAC Monitors

During the regular monitoring of the stitching centres, the IMAC monitoring teams also try to assess the physical conditions at the stitching centers such as sufficient sitting space for stitchers, light, sitting arrangements, ventilation/ air circulation, drinking water availability and toilets. However, while collecting the information cultural norms and social aspects are kept in view.  Generally three categories are used for these assessment: 1:  Excellent/ More than sufficient, 2:  Good/ sufficient; 3: Poor/ insufficient/not available. The stitching centres are classified into two types i.e. Purposely Built Centres and others. The Purposely Built Centres are monitored for two additional conditions i.e. Fire Extinguisher and First Aid facilities. During the reporting period, 1,629 centers were visited. The working conditions of 325 centers observed in the monitoring visits are  given in the following paragraphs:

Space:	146 stitching centers visited had more than enough space and 176 had enough space. IMAC monitors found only 3 centers where stitchers were sitting clumsily.

Lights:	256 stitching centers were well lit whereas 67 stitching centre had reasonably good lighting system such as bulbs and windows. 2 centers had poor lighting arrangements.

Ventilation:	236 stitching centers were found having good ventilation and air circulation system like high roofs, large doors and windows; 87 stitching centers had somewhat average conditions; only 2 centers had poor ventilation.

Drinking

Water:          322 stitching centers had drinking water available whereas in 3 centers water for drinking was not 		available to the stitchers.

Toilets:	236 stitching centers had proper toilets facilities i.e. one toilet available for thirty stitchers; at 31 stitching centers toilets were available but not sufficient and 58 stitching centers did not have any toilet facilities.

Sitting

Arrangement:  In 256 centers, the sitting arrangement was good i.e. the stitchers were using a chair or a chowki and mat, at 65 centers stitchers were sitting on a chaoki. Only 4 centers were found with poor sitting arrangements.

General

Hygiene :	138 centers were found in good hygienic conditions. In 178 centers, the hygienic conditions were average whereas in 9 centers, it was poor.

Fire

Extinguisher:   IMAC monitors visited 56 centers, purposely built by the manufacturers, out of which 49 centers had fire extinguishers whereas 7 stitching centers had no such facility.

First Aid:	Out of 56 purposely-built centers, in 45 stitching centers first aid box was available in case of emergencies and the stitchers or the subcontractor knew how to use it. 6 centers have such facility but no one knew how to use it, 5 centers had no such facility.

The conditions of the rest of 1,304 visited centers have not been included because of the following reasons:-

- 875 of them were village based centers and their conditions are not monitored because they are almost always the same;

- 350 centers were found closed either due to non availability of material or harvesting season or sub-contractors’ personal reasons;

- 67 centers were found permanently closed because their sub-contractor had left the work;

- 12 centers were in the process of being established;