Independent Monitoring Association for Child Labour (IMAC)

#### Seventy Second Progress Report

(01 March 2009 –    31 March 2009)

General:

Since the beginning of the programme, so far, in total 141 sports ball manufacturers joined the Child Labour Elimination Programme (CLEP). However 50 manufacturers had left the programme on different occasions due to the non-payment of their dues to the SCCI or some other reasons. As such 91 soccer ball manufacturers are present in the programme at the moment. From this, 63 manufacturers are in IMAC’s main database whereas 28 are in the provisional list.

Monitoring Progress:

During the month of March 2009 there were 1,829 stitching centers operational and registered with IMAC. Of these IMAC monitored 1,468 stitching centers pertaining to 49 manufacturers. This included 3 manufacturers from the list of provisional members. Altogether 28 manufacturers are in the provisional list. Among the 28 provisional members, 25 manufacturers are not active as they do not have any work in hand and their monitoring is stopped.

Of the total 1,829 operational centers, 106 were small village-based centers, 724 were exclusively female centers, 252 were combined and rest of the 747 centers were male centers. During March 2009, out of the 1,468 centers visited, 564 were male centers, 615 were female centers, 201 were combined and 88 were small village based centers. While visiting the stitching centres outside Sialkot district, the IMAC monitored 104 centers of 21 manufacturers with 1,097 stitchers located in the districts of Gujranwala, Gujrat, Narowal, Hafiz Abad and Sheikhupura.

Based on the IMAC criterion of ABC performance list, 62 manufacturers, are placed in the category “A”, one manufacturer i.e. M/S Orpheus Enterprises (Pvt) Ltd. maintained their status in Category “C”.

Working Conditions in the Stitching Centres Monitored by IMAC Monitors:

During the regular monitoring of the stitching centres, the IMAC monitoring teams also try to assess the physical conditions at the stitching centers such as sufficient sitting space for stitchers, light, sitting arrangements, ventilation/ air circulation, drinking water availability and toilets. However, while collecting these information cultural norms and social aspects are kept in view.  Generally three categories are used for these assessment: 1:  Excellent/ More than sufficient, 2:  Good/ sufficient; 3: Poor/ insufficient/not available. The stitching centres are classified into two types i.e. Purposely Built Centres and others. The Purposely Built Centres are monitored for two additional conditions i.e. Fire Extinguisher and First Aid facilities. As a policy measure, IMAC does not monitor working conditions of house based stitching centres. Therefore, 88 village based / house based centres visited in March 2009 are excluded for monitoring working conditions. As such, for working conditions, IMAC monitors monitored 1380 stitching centres.

Of these, IMAC monitors found 797 stitching centres either closed due to variety of reasons or found stitchers sitting idle as at the time of the visit the stitchers did not have enough material to stitch. As such IMAC monitors could verify the working conditions of only 583 centres. The details of the working conditions of the centres observed in the monitoring visits are given in the following paragraphs:

Space:	484 stitching centres visited had more than enough space and 99 had enough space.

Problems: None

Lights:	485 stitching centres were well lit whereas 98 stitching centres had reasonably good lighting system such as bulbs and windows.

Problems: None

Ventilation:	494 stitching centres were found having good ventilation and air circulation system like high roofs, large doors and windows; 89 stitching centres had somewhat average conditions.

Problems: None

Drinking

Water:           	583 stitching centres had drinking water available to the stitchers.

Problems:  None

Toilets:	482 stitching centres had proper toilets facilities i.e. one toilet available for thirty stitchers; at 101 stitching centres toilets were available but not sufficient.

Problems:  None

Sitting

Arrangement:  In 432 centres, the sitting arrangement was good i.e. the stitchers were using a chair or a chowki and mat, at 151 centres stitchers were sitting on a chaoki.

Problems: None

General

Hygiene:	217 centers were found in good hygienic conditions whereas in 366 centres, the hygienic conditions were average.

Problems:  None

Fire

Extinguisher:  	IMAC monitors visited 86 centres, purposely built by the manufacturers, out of which 81 centres had fire extinguishers.

Problems: 5 stitching centres had no such facility.

First Aid:	Out of 86 purposely-built centres, in 60 stitching centres first aid box was available in case of emergencies and the stitchers or the subcontractor knew how to use it. 16 centres have such facility but no one knew how to use it.

Problems: 10 stitching centres had no such facility.

Violations Identified During March 2009:

In the month of March 2009, respective manufacturers were asked for explanation about the violations of the programme provisions, as follows:

1 -   22 Manufacturers for Un-registered stitching activities.

2 -    3  Manufacturers for non-printing of ID Code.

3 -    3  Manufacturers for poor working conditions.

Responses of Manufacturers on violations identified During March 2009:

- Un-registered Stitching Activities:

Problems: During March 2009, 22 manufacturers were identified with un-registered stitching activities.

Responses received so far are as follows:

  - 5 Manufacturers admitted that the material was leaked from the registered centre. These manufacturers took strict action against the sub-contractors who had leaked out the material and stopped working with the sub-contractors.

  - 16 Manufacturers have issued warnings to their sub-contractor(s) responsible for the violation.

  - Response from the remaining 1 Manufacturer is awaited.

- Non-printing of ID Code:

Problems: During March 2009, 3 Manufacturers were identified with non-printing of ID Codes.

Responses:

  - One manufacturer has replied that the mentioned work did not belong to him.

  - Responses from the other two manufacturers are awaited.

- Working Conditions:

Problems: During March 2009, 3 manufacturers were identified having no first aid boxes and fire extinguishers at some of their stitching centres.

Responses:

  - Two manufacturers have cleared the complaints regarding poor working conditions.

  - Response from the remaining one Manufacture is awaited.

Late responses received of February violations:

1.  Un-registered Stitching Activities:

The remaining three manufacturers have issued warnings to their sub-contractor(s) responsible for the violation.

2. Working Conditions:

The remaining two manufacturers have cleared the complaints regarding poor working conditions.