Independent Monitoring Association for Child Labour (IMAC)

#### One Hundred & Thirty Forth Progress Report

(01 June 2014 – 30 June 2014)

General:

Since the beginning of the programme, so far, in total 158 sports ball manufacturers joined the Child Labour Elimination Programme (CLEP). However 101 manufacturers had left the programme on different occasions due to the non-payment of their dues to the SCCI or some other reasons. As such 57 soccer ball manufacturers are present in the programme at the moment. From this, 46 manufacturers are in IMAC’s main database whereas 11 are in the provisional list.

Monitoring Progress:

During the month of June, 2014 there were 2,032 stitching centers operational and registered with IMAC. Of these IMAC monitored 1,294 stitching centers pertaining to 43 manufacturers. This included 9 manufacturers from the list of provisional members. Altogether 11 manufacturers are in the provisional list.

Of the total 2,032 operational centers, 9 were small village-based centers, 1,023 were exclusively female centers, 351 were combined centres, 609 were male centers and rest of the 40 were stores used for distribution of balls material for the stitching purposes.

During June, 2014, out of the 1,294 centers visited, 6 were small village-based centers, 708 were exclusively female centers, 219 were combined centres, 334 were male centers and rest of the 27 were stores. While visiting the stitching centres outside Sialkot district, the IMAC monitored 228 centers of 22 manufacturers with 1,879 stitchers located in the districts of Gujranwala, Gujrat, Narowal, Hafiz Abad, Sheikhupura and Lahore.

In the month of June, 2014 one manufacturer i.e.  Kapur (Pvt) Ltd.  has left the program.

Based on the IMAC criterion of ABC performance list, 46 manufacturers are placed in the category “A”.

Working Conditions in the Stitching Centres Monitored by IMAC Monitors:

During the regular monitoring of the stitching centres, the IMAC monitoring teams also try to assess the physical conditions at the stitching centers such as sufficient sitting space for stitchers, light, sitting arrangements, ventilation/ air circulation, drinking water availability and toilets. However, while collecting these information cultural norms and social aspects are kept in view.  Generally three categories are used for these assessment: 1:  Excellent/ More than sufficient, 2:  Good/ sufficient; 3: Poor/ insufficient/not available. The stitching centres are classified into two types i.e. Purposely Built Centres and others. The Purposely Built Centres are monitored for two additional conditions i.e. Fire Extinguisher and First Aid facilities. As a policy measure, IMAC does not monitor working conditions of house based stitching centres and stores. Therefore, 6 village based / house based centres and 27 stores visited in June, 2014 are excluded for monitoring working conditions. As such, for working conditions, IMAC monitors monitored 1,261 stitching centres.

Of these, IMAC monitors found 749 stitching centres either closed due to variety of reasons or found stitchers sitting idle as at the time of the visit the stitchers did not have enough material to stitch. As such IMAC monitors could verify the working conditions of only 512 centres. The details of the working conditions of the centres observed in the monitoring visits are given in the following paragraphs:

Space:	510 stitching centres visited had more than enough space and 2 stitching centres visited had enough space.

Problems: None

Lights:  	512 stitching centres were well lit.

Problems: None

Ventilation:	511 stitching centres were found having good ventilation and air circulation system like high roofs, large doors and windows; 1 stitching centre had somewhat average conditions.

Problems: None

Drinking	512 stitching centres had drinking water available to the stitchers.

Water:           	Problems: None

Toilets:	504 stitching centres had proper toilets facilities and 8 stitching centres had toilets available but not sufficient.

Problems: None

Sitting

Arrangement:  In 512 centres, the sitting arrangement was good.

Problems: None

General

Hygiene:	416 centers were found in good hygienic conditions whereas in 96 centres, the hygienic conditions were average.

Problems: None

Fire

Extinguisher:  	IMAC monitors visited 39 centres, purposely built by the manufacturers, 34 centres had fire extinguishers available and 3  centres had fire extinguishers available  but not updated.

Problems: Two centres had no such facility.

First Aid:	Out of 39 purposely-built centres, in 32 stitching centres first aid box was available in case of emergencies and the stitchers or the subcontractor knew how to use it. 5 centres had such facility available but empty.

Problems:  Two centres had no such facility.

Violations Identified During June, 2014

In the month of June, 2014 respective manufacturers were asked for explanation about the violations of the programme provisions, as follows:

Un-registered Stitching Activities:

Problems: 	During June 2014, 13 manufacturers were identified with un-registered stitching activities.

Responses:	10 manufacturers have issued warnings to the sub contractors responsible for the violation occurred.

02 manufacturers took serious action against the sub contractor responsible for the violation and stopped working with him.

01 manufacturer did not respond. Reminder has been issued to that manufacturer.

Non Printing of ID Code:

Problems:    During June 2014, 6 manufacturers were identified with this violation.

Responses:  All these manufacturers have issued warning to the printing staff responsible for the violation occurred.

Working Conditions:

Problems: 	One manufacturer was identified having no fire extinguisher and first aid box at the stitching centres.

Responses:  The manufacturer has responded to make available the provision of the same at such stitching centres.